## 2019-2024 Final
CHAPTER | SECTION | SUB-SECTION | WESTERN WASHINGTON PHASE II MUNICIPAL STORMWATER PERMIT IMPLEMENTATION SCHEDULE
[5 empty] | 2013 |  |  |  |  | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
|  |  | TASKS | DEPT / DIV | August 1st | September | October | November | December 1 | January | February 16 | March 31 | April | May | June | July | August 15 | September | October | November | December | January 1 | February 16 | March 31 | April | May 31 | June | July | August | September | October | November | December | January | February 2 | March 31 | April | May 31 | June | July | August | September | October | November | December 31 | January 1st | February | March 31 | April | May 31 | June | July | August 1st | September | October | November | December | January | February 2 | March 31 | April | May 31st | June | July 31st | August | September | October | November | December | January 1st | February | March | April | May | June | July | August 1 | September | October | November | December | January 1 | February | March | April 30 | May | June | July | August | September | October | November | December | January 1 | February 1 | March | April 1 | May | June | July | August 1 | September | October | November | December | January 1 | February | March | April | May | June | July | August | September | October | November | December | January 1 | February | March | April | May | June | July | August | September | October | November | December | January 1 | February | March 31 | April | May | June | July | August 1 | September | October | November | December
S5 | A1 |  | SWMP (Stormwater Management Program) Develop & Implement
| A2 |  | SWMP Plan Annually Updated
| A3 | a. | Track Costs or Estimated Costs
|  | b. | Track Inspections, Enforcements & Public Educ. Activities
| A4 |  | Continue Implementation of Existing Programs
| A5 | a. | Include Coord. Mech. with Other Entities (If Applicable)
|  | b. | SWMP Includes Internal Coordination Mechanisms
| C1 |  | Stormwater Planning
|  | a. | Convene Interdisiplinary Team
|  | b. | Coordination with long-range plan updates
|  | b.i. | Watershed protection policies, strategies, codes and measures report
|  | b.i.(a) | Describe how WQ and watershed protection were addressed in the 2013-2019 permit cycle
|  | b.i.(b) | Describe how WQ and watershed protection are being addressed in the current permit cycle
|  | c. | Low Impact Development code-related requirements
|  | c.i | Continue to require LID
|  | c.i.(a) | Annually assess and report new admin or regulatory barriers to LID
|  | c.ii | Review and revise LID codes. Incl. summary in 2024 rpt
|  | c.ii.(a) | Measures to minimize impervious surfaces
|  | c.ii.(b) | Measures to minimize loss of native vegetation
|  | c.ii.(c) | Other measures to minimize stormwater runoff
|  | d | Stormwater Management Action Planning
(Long term MS4 planning to protect and recover receiving waters)
|  | d.i | Receiving water basin assessment
|  | d.i | Methods/procedure for identifying and characterizing basins
|  | d.i | 1. Convene and interdisciplinary team to conduct and coordinate the effort.
|  | d.i | 2. Delineate basin boundaries for all receiving waters in your jurisdiction with approximately between 1 -10 square mile total watershed areas.
|  | d.i | 3. Provide an interim report.
|  | d.i | 4. For basins in which you have at least 10% of the total watershed area or which you are partnering with another jurisdiction: a. Compile existing information to inform understanding of receiving water condition and or impairment to beneficial uses. b. Conduct a qualitative (or quantitative) assessment of each receiving water. Identify data gaps and develop a strategy to address data needs.
|  | d.i | 5. Deliverable: (year TBD) Watershed inventory with key characteristics of each basin and, if applicable, GIS coverage with your refined basin delineations, prioritization and ranking.
|  | d.i.(a) | Identify basins with low influence on SMAP
|  | d.ii | Receiving water basin prioritization
|  | d.ii | Methods/procedure for prioritizing basins
|  | d.ii | 1. For each basin, identify whether the receiving water show low to moderate levels of impairment (e.g., as assessed via water quality data, B-IBI scores, habitat surveys).
|  | d.ii | 2. Prioritize watersheds in need of protection.
|  | d.ii.(a) | Document the priority ranking process
|  | d.ii.(a) | Approach/methods for catchment area planning
|  | d.ii.(a) | Develop a long-term MS4 plan for the catchment areas (receiving water body subbasins approximately 400-600 acres in size) which they identify in their priority basins.
|  | d.ii.(a) | 1. Share the results of your prioritization process and engage your interdisciplinary team in identifying which catchment areas will be your focus for long-term MS4 planning. a. Include public/citizen representation and involvement in this process.
|  | d.ii.(a) | 2. For TBD of your top priority basins, identify TBD catchment areas for planning.
|  | d.ii.(a) | 3. Identify actions that are most likely to improve hydrologic and water quality conditions.
|  | d.ii.(a) | 4. Conduct a public review process and have discussions with planning officials throughout the process.
|  | d.ii.(a) | 5. Develop an effectiveness assessment to provide feedback on the implementation efforts.
|  | d.ii.(a) | 6. Deliverable in year TBD of permit: proposed plan (including rationale for selected BMPs/actions) and estimated budget/funding approach.
|  | d.ii.(b) | ID and rank areas where receiving waters would benefit from retrofits and targeted implementation
|  | d.iii | Develop SMAP (Stormwater Management Action Plan) for at least one high priority area that identifies:
|  | d.iii.(a) | Desc. of needed facility retrofit, BMPs and locations
|  | d.iii.(b) | Land mgmt/development strategies
|  | d.iii.(c) | Targeted, enhanced or customized impl. of SW mgmt actions
|  | d.iii.(d) | Identify needed changes to long range plans
|  | d.iii.(e) | Proposed Implementation Schedule and budget for: Short-term actions (Less than 6 years), and Long-term actions (7-20 years)
|  | d.iii.(f) | Process to assess and provide feedback on planning process, implementation and projects.
| C2 |  | Public Education & Outreach
|  | a. | Program based on Local WQ and Demographics
|  | a.i | General Awareness - Annually select 1 target audience and 1 subject from either S5.C2.a.i (a) or (b)
|  | a.i.(c) | Provide information to target audience on an ongoing or strategic schedule
|  | a.ii | Behavior Change - Select 1 target audience and 1 BMP from S5.C2.a.ii(a)
|  | a.ii.(b). | Evaluate Behavior Change program from 2013-2019 permit
|  | a.ii.(c) | Based on evaluation, develop social media marketing program tailored to community using Community-Based Social Marketing.
|  | a.ii.(c)1 | Dev. strategy and sch. to effectively implement ex. prog., or
|  | a.ii.(c)2 | Dev. strategy and sch. to expand ex. prog. to new audience or BMPs, or
|  | a.ii.(c)3 | Dev. strategy and sch. for new target audience and BMP behavior change campaign
|  | a.ii.(d) | Begin to implement strategy from S5.C2.a.ii.(c)
|  | a.ii.(e) | Evaluate and report on changes in understanding and adoption and planned or recommended changes to campaign.
|  | a.ii.(f) | Use evaluation results to direct ongoing behavior change program
|  | a.iii | Create Stewardship Opportunities
| C3 |  | Public Involvement and Participation
|  | a. | Create Opportunities for Public Participation
|  | b. | SWMP & Annual Report Website Posting
| C4 |  | MS4 Mapping and Documentation
|  | a. | Ongoing Stormwater Mapping - periodically update
|  | a.i | Update known MS4 outfalls and discharge points
|  | a.ii | Update receiving waters
|  | a.iii | SW treatment and flow ctrl BMPs/facilities owned or operated by Permittee
|  | a.iv | Geographic areas served by Permittee's MS4 that do not discharge to surface waters
|  | a.v | Tributary conveyances to all known outfalls 24" diameter or equivalent:
|  | a.v.(a) | Tributary conveyance type, material and size
|  | a.v.(b) | Associated drainage areas
|  | a.v.(c) | Land use
|  | a.vi | Connections between MS4 and other public entities
|  | a.vii | Map All New Connections Since February 16, 2007
|  | b | New Mapping
|  | b.i | Map size and material for all known MS4 outfalls
|  | b.ii | Map all known connections from MS4 to private storm systems
|  | c. | All mapping to be electronic fully described mapping standards
|  | d. | Make maps available to Ecology upon request
|  | e. | Make maps available to tribe, municipalities or Permittees upon request
| C5 |  | Illicit Discharge Detection & Elimination Program
|  | a. | Include procedure for reporting, or removing illicit connections, spills or discharges
|  | b. | Inform public employees, businesses and general public of hazards of illicit discharges
|  | c. | Implement ordinance to prohibit non-stormwater illicit discharges
|  | c.iv | Ordinance shall include escalating enforcement
|  | d. | Implement program to detect illicit discharges
|  | d.i.a | Field screen 12% of MS4 each year
|  | d.ii | Publicly List Phone #'s for Reporting Spills
|  | d.iii | Ongoing Training all Muni. Field Staff
|  | e. | Ongoing IDDE Program to include:
|  | e.i | Procedures to characterize illicit discharge
|  | e.ii | Procedures to trace illicit discharge
|  | e.iii | Procedures for eliminating illicit discharges
|  | e.iv | Compliance = respond, investigate, eliminate w/i 6 months
|  | f. | Staff IDDE training
|  | g. | Track and keep records of IDDE Program in WQWebIDDE format
| C6 |  | Controlling Runoff from New Development, Redevelopment and Construction Sites
|  | a. | Update Construction Site Runoff Ordinance
|  | a.i | Apply program (S5.C6.b.(i) through (iii) to projects submitted after 07/01/2022
|  | a.ii | Apply program to projects submitted prior to 01/01/2017 that have not started work by 01/01/2022
|  | a.iii | Apply program to projects submitted prior to 07/01/2022 that have not started work by 01/01/2022
|  | b. | The ordinance shall include:
|  | b.i | Site Plan & BMP Select per Append 1 or Approved Ph I
|  | b.ii | Implement MRs in Appendix 1
|  | b.iii | Ord./ Reg. Mech. Giving Legal Authority to Inspect Pvt Facilities
|  | c. | Implement permitting process with site plan review, inspection and enforcement to meet S5.C6.b.i
|  | c.i | Review All Stormwater Site Plans
|  | c.ii | Pre-Con Site Inspection (of sites w/ high potential for sediment transport)
|  | c.iii | Inspect All Sites for Erosion and Sediment Controls
|  | c.iii | Enforce ESC as necessary
|  | c.iv | Final ESC and SW Facility Inspection
|  | c.iv | Maintenance Plan for New Facilities
|  | c.iv | Enforce Maintenance Plan
|  | c.v | Insp. all dev. sites upon completion
|  | c.vi | Minimum Compliance = 80% Scheduled Inspections
|  | c.viii | Maintain records of site visits, insp rpts, letters, etc.
|  | c.viii | Implement enforcement strategy for non-compliance
|  | d. | Make NOI for Const. & Industrial Site Avail. & Enforce Local Regs on NPDES Const. Sites
|  | e. | Train All Applicable Staff on Above Activities (Track)
| C7 |  | Operations and Maintenance (for Municipally Owned or Operated)
|  | a. | Update Maint. Stnds to SWMMWW
|  | a.ii | Perform Timely Maintenance
|  | b. | O&M for Private Stormwater Facilities and BMPs.
|  | b.i. | Verify long term O&M of SW treatment and flow ctrl BMPs
|  | b.i.(a) | Implement ordinance to ID party responsible for maintenance, reqs inspection and enforcement
|  | b.i.(b) | Annually Inspect All Pvt. Treatment & Flow Ctrl. Facilities
|  | b.i.(c) | Inspect Bonded Resid. Facilities Every 6 Months until 90% of lots constructed (or when construction stops and sites are fully stabilized)
|  | b.ii | Compliance = records + 80% scheduled inspections
|  | b.iii | Track Inspections, Enforcements etc. (All Notices)
|  | c. | Operations and Maintenance (for Municipally Owned or Operated Stormwater Facilities)
|  | c.i | Annually Inspect All Public Treatment & Flow Ctrl. Facilities
|  | c.ii | Spot Check Inspections After Major Storms (10 yr 24 Hour)
|  | c.iii | Catch Basin Insp. & Maintenance. - every 2 yrs | [74 empty] | 2 year schedule (ongoing)
|  | c.iv | Ensure 95% compliance for O&M inspections
|  | d. | Establish & Implem. Practices to Reduce Impacts
|  | e. | O&M Training Program (Train to Standards)
|  | f. | SWPPPs for All Heavy Equip. Mnt. & Storage Yards
|  | g. | Track Maint. & Repair Activities Identified Above
| C8 |  | Source Control Program for Existing Development
|  | a. | Implement program to prevent and reduce pollutants in runoff
|  | a.i | Apply operational, structural and treatment BMPs to pollution generating existing uses
|  | a.ii | Inspect public and private commercial and industrial properties
|  | a.iii | Apply and enforce local ordinances at sites identified in S5.C.8.b.ii
|  | a.iv | Implement practices to reduce polluted runoff from pesticides, herbicides and fertilizer at Permittee owned or operated sites
|  | b. | Minimum Performance Measures
|  | b.i | Adopt and enforce ordinance requiring application of source ctrl BMPs associated with existing land uses
|  | b.ii | Establish inventory of public and private commercial and industrial properties including:
|  | b.ii(a) | Include businesses based on pollution generating activities
|  | b.ii(b) | Complaint based response (mobile or home based businesses, and multifamily properties)
|  | b.iii | Implement inspection program of sites from S5.C8.b.ii
|  | b.iii(a) | Provide source ctrl requirement information to all businesses with a business address based on activities
|  | b.iii(b) | Annually inspect at least 20% of businesses on source ctrl inventory
|  | b.iii(c) | Inspect 100% of sites identified through legitimate complaints
|  | b.iv | Implement progressive enforcement policy
|  | b.iv(a) | Take follow-up actions on sites failing inspections or to adequately implement BMPs
|  | b.iv.(b) | If business does not adequately implement BMPs after follow-up actions, take enforcement action as established in code and ordinances or judicial system
|  | b.iv.(c) | Maintain records of site visits, insp rpts, letters, etc.
|  | b.iv(d) | Refer non-emergency violations to DOE if progressive enforcement does not yield results
|  | b.v | Train staff for inspection, enforcement and related tasks
S8 |  |  | Monitoring & Assessment
| A |  | Regional Status and Trends Monitoring
|  | 1 | For permittiees that chose S8.B Status and Trends Monitoring Option #1 in the 2013 Permit (N/A for COBG)
|  | 2 | Regional Status and Trends Monitoring Notification to DOE
|  | 2.a | Annual Status and Trends Monitoring Contribution (COBG $4,974)
|  | 2.b | Conduct Discharge Monitoring (N/A for COBG)
| B |  | SWMP Effectiveness and Source ID studies | [6 empty] | Notification to DOE | [7 empty] | Annual Payments Start
|  | 1 | Effectiveness Monitoring Contribution (See S8.B.2.a)
|  | 2 | Effectiveness and Source ID Notification to DOE
|  | 2.a | Annual Contribution to SAM Effectiveness and source ID studies ($6,158 for COBG)
|  | 2.b | Stormwater Discharge Monitoring (N/A for COBG)
| C |  | Stormwater Discharge Monitoring (N/A for COBG) | [6 empty] | Notification to DOE | [7 empty] | Annual Payments Start
S9
| A-D |  | Annual Compliance Report
G18 | [51 empty] | `
Apply for permit renewal
|  |  | LEGEND: |  |  |  | Effective & Expiration Dates of Permit | [22 empty] | Ongoing Requirement | [14 empty] | Permit Deadline | [33 empty] | Effective & Expiration Dates of Permit
Ongoing Requirement
Permit Deadline
Prep Work