## Schedule
2019-2024 NPDES Permit - Stormwater Management Action Planning
Implementation Schedule
Permit Section S.5 - Stormwater Planning |  |  |  | 2019 |  |  |  |  | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [10 empty] | Status as of: | __/__/__
Sub-Section C.1. | Permit to Appendix Cross Reference | Compliance Action (Refer to Permit for full text) | Permit Due Date | August 1 | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July 31 | Responsible Department | Responsible Program | Responsible Staff | Target Due Date | Status | Date Completed | SWMP Cross Reference | Notes
a. | App. 3: Q5 | Convene a team to inform and assist in the development, progress, and influence of stormwater planning program. | 2020-08-01 | [12 empty] | 1 | [50 empty] | 2020-08-01
b.i.a. | App. 3: Q6, Q7, Q8, Q9, Q10, Q10a, Q11, Q11a, Q12, Q12a, Q12b, Q12c, Q13, Q14 | Describe for the previous permit term (2013-2019) how stormwater management needs and protection/improvement of receiving water health did (or did not) inform the planning update process and influenced policy and strategies (e.g., updates to Comprehensive Plan or other long-range land use plans used to accommodate growth or transportation). | 2021-03-31 | [19 empty] | 31 | [43 empty] | 2021-03-31
b.i.b. | App. 3: Q6, Q7, Q8, Q9, Q10, Q10a, Q11, Q11a, Q12, Q12a, Q12b, Q12c, Q13, Q14 | Describe (via a report) how stormwater management needs and protection/improvement of receiving water health are (or are not) informing the planning update process and influencing policy and strategies since August 1, 2019 (e.g., updates to Comprehensive Plan or other long-range land use plans used to accommodate growth or transportation). | 2023-01-01 | [41 empty] | 1 | [21 empty] | 2023-01-01
c.i. | App. 3: Q15, Q16, Q16a; App. 1; App. 10 | Continue to require LID Principals and BMPs when updating, revising, and developing new local development codes, rules, standards, and other enforceable documents. Make LID the preferred and commonly-used approach to site development. | Ongoing | [63 empty] | Ongoing
c.i.a. | App. 3: Q16, Q16a | Assess and document any newly identified admin or regulatory barriers to LID implementation. Describe (if any) mechanisms adopted to encourage or require implementation of LID principals or BMPs. | Annually | [7 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [11 empty] | 31 | [7 empty] | Annually
d.i. | App. 3: Q17, Q17a | Receiving Water Assessment: Document and assess existing info related to local receiving waters and contributing area conditions to identify receiving waters most likely to benefit from stormwater management planning. Submit a watershed inventory to Ecology in table format, with contents described in this permit section and the guidance document. Include assessment documentation. | 2022-03-31 | [31 empty] | 31 | [31 empty] | 2022-03-31
d.ii. | App. 3: Q18, Q18a | Receiving Water Prioritization: Develop and implement a prioritization method and process to determine which receiving waters will receive the most benefit from the retrofits, SWMP actions, and other land/development management actions. Rank the list and document the method and ranking process used in a report format. | 2022-06-30 | [34 empty] | 30 | [28 empty] | 2022-06-30
d.iii. | App. 3: Q19, 19a | Develop a SMAP for at least one high priority catchment area from the Receiving Water Prioritization process that identifies: a) Stormwater facility retrofits needed,; b) Land management/development strategies and/or actions for water quality management; c) Targeted, enhanced, or customized implementation of stormwater actions related to S5; d) Changes needed to local long-range plans; e) Implementation schedule and budget for short-term and long-term actions; f) Process and schedule for future assessment and feedback to improve planning process and implementation of procedures or projects. Submit to Ecology. | 2023-03-31 | [43 empty] | 31 | [19 empty] | 2023-03-31
[5 empty] | LEGEND | [5 empty] | Prep Work (estimated) | [12 empty] | Permit Deadline

## Action Status
NPDES Permit Implementation Schedule - Stormwater Management Action Plan (SMAP)
Permit Section S5 - Stormwater Planning
Assignments and Status | [5 empty] | Status as of:____/____/____
Sub-Section C.1. | Permit Cross Reference | Compliance Action (Refer to permit for full text) | Permit Due Date | Responsible Department(s) | Responsible Staff | Status | Date Complete | Notes
a. | App. 3: Q5 | Convene a team to inform and assist in the development, progress, and influence of stormwater planning program. | 2020-08-01
b.i.a. | App. 3: Q6, Q7, Q8, Q9, Q10, Q10a, Q11, Q11a, Q12, Q12a, Q12b, Q12c, Q13, Q14 | Describe for the previous permit term (2013-2019) how stormwater management needs and protection/improvement of receiving water health did (or did not) inform the planning update process and influenced policy and strategies (e.g., updates to Comprehensive Plan or other long-range land use plans used to accommodate growth or transportation). | 2021-03-31
b.i.b. | App. 3: Q6, Q7, Q8, Q9, Q10, Q10a, Q11, Q11a, Q12, Q12a, Q12b, Q12c, Q13, Q14 | Describe (via a report) how stormwater management needs and protection/improvement of receiving water health are (or are not) informing the planning update process and influencing policy and strategies since August 1, 2019 (e.g., updates to Comprehensive Plan or other long-range land use plans used to accommodate growth or transportation). | 2023-01-01
c.i. | App. 3: Q15, Q16, Q16a; App. 1; App. 10 | Continue to require LID Principals and BMPs when updating, revising, and developing new local development codes, rules, standards, and other enforceable documents. Make LID the preferred and commonly-used approach to site development. | Ongoing
c.i.a. | App. 3: Q16, Q16a | Assess and document any newly identified admin or regulatory barriers to LID implementation. Describe (if any) mechanisms adopted to encourage or require implementation of LID principals or BMPs. | Annually
d.i. | App. 3: Q17, Q17a | Receiving Water Assessment: Document and assess existing info related to local receiving waters and contributing area conditions to identify receiving waters most likely to benefit from stormwater management planning. Submit a watershed inventory to Ecology in table format, with contents described in this permit section and the guidance document. Include assessment documentation. | 2022-03-31
d.ii. | App. 3: Q18, Q18a | Receiving Water Prioritization: Develop and implement a prioritization method and process to determine which receiving waters will receive the most benefit from the retrofits, SWMP actions, and other land/development management actions. Rank the list and document the method and ranking process used in a report format. | 2022-06-30
d.iii. | App. 3: Q19, 19a | Develop a SMAP for at least one high priority catchment area from the Receiving Water Prioritization process that identifies: a) Stormwater facility retrofits needed,; b) Land management/development strategies and/or actions for water quality management; c) Targeted, enhanced, or customized implementation of stormwater actions related to S5; d) Changes needed to local long-range plans; e) Implementation schedule and budget for short-term and long-term actions; f) Process and schedule for future assessment and feedback to improve planning process and implementation of procedures or projects. Submit to Ecology. | 2023-03-31

## Appendix 3 - Qs
Permit Condition | Sub-Section | Permit Section | Permit Cross Reference | Compliance Action | Responsible Department | Responsible Program | Responsible Staff | Target Due Date | Status | Date Completed | SWMP Cross Reference | Notes
Appendix 3 | Q1 | Annual Report Questions for Cities, Towns and Counties | S9.D.6. | Attach a copy of any annexations, incorporations, or boundary changes resulting in an increase or decrease in the Permittee’s geographic area of permit coverage during the reporting period per S9.D.6.
Appendix 3 | Q2 | Annual Report Questions for Cities, Towns and Counties | S5.A.2.; S9.A.; S9.D1. | Attach updated annual Stormwater Management Program Plan (SWMP Plan). (S5.A.2)
Appendix 3 | Q3 | Annual Report Questions for Cities, Towns and Counties | S5.A.3.; S5.A.3.a. | Implemented an ongoing program to gather, track, and maintain information per S5.A.3, including costs or estimated costs of implementing the SWMP.
Appendix 3 | Q4 | Annual Report Questions for Cities, Towns and Counties | S5.A.5.b. | Coordinated among departments within the jurisdiction to eliminate barriers to permit compliance. (S5.A.5.b)
Appendix 3 | Q4a | Annual Report Questions for Cities, Towns and Counties | S5.A.5.b. | Attach a written description of internal coordination mechanisms. (S5.A.5.b)
Appendix 3 | Q5 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.a. | Have you convened an interdisciplinary team to inform and assist in the development, progress, and influence of the stormwater planning program? (S5.C.1.a. – Required by August 1, 2020)
Appendix 3 | Q6 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | List the relevant land use planning efforts that have taken place in your jurisdiction (land use plans that are used to accommodate growth, stormwater management, or transportation). (S5.C.1.b.i(a) and (b) – Required by March 31, 2021 & January 1, 2023)
Appendix 3 | Q7 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | List of stormwater capital projects (currently in or slated for future design and construction) that resulted from this planning. (S5.C.1.b.i(a) and (b) – Required by March 31, 2021 & Jan 1, 2023)
Appendix 3 | Q8 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Describe of watershed protection measures associated with stormwater management and land use planning actions that resulted from this planning. (S5.C.1.b.i(a) and (b) – Required by March 31, 2021 & January 1, 2023)
Appendix 3 | Q9 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Were land acquisitions identified (or are planning ahead for) that are useful for stormwater facilities to: accommodate growth or to better serve an existing developed area? (S5.C.1.b.i(a) and (b) – Required by March 31, 2021 & January 1, 2023)
Appendix 3 | Q9a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | If yes, for what purpose?
Appendix 3 | Q10 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Identified corrective actions, in addition to the minimum requirements of the Municipal Stormwater Permits to control or treat municipal stormwater discharges that pollute waters of the State (e.g. Limits to impervious cover added to any zoning districts, regional facility planning, minimization of vegetation loss, etc.)? (S5.C.1.b.i(a) and (b) – Required by March 31, 2021 & January 1, 2023)
Appendix 3 | Q10a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | If yes, briefly describe and list relevant plan or code sections, if applicable.
Appendix 3 | Q11a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Updates to goals and policies related to investment in stormwater management facilities/BMPs? (yes/no) (S5.C.1.b.i(a) and (b) – Required by March 31, 2021 & January 1, 2023)
Appendix 3 | Q11a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | If yes, briefly describe.
Appendix 3 | Q12 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Does the long-range plan identify the location and existing capacity of the stormwater facilities owned or operated by the Permittee and show which of those stormwater facilities have unused capacity? (S5.C.1.b.i(a) and (b) – Required by March 31, 2021 & January 1, 2023)
Appendix 3 | Q12a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Do these stormwater facility locations impact where housing, or other types of development, are projected to be located or influence the acquisition of land? (If yes, how?)
Appendix 3 | Q12b | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Does the long-range plan identify a lack of facilities and the potential impacts of existing or new development to those areas and receiving waters?
Appendix 3 | Q12c | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Any new proposed locations and capacities of stormwater facilities needed for the timeframe of the plan?
Appendix 3 | Q13 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Based on the projected population densities and distribution of growth over the planning period, describe how stormwater runoff impacts are forecasted. Does stormwater management information (including water quality) direct where growth is directed? (S5.C.1.b.i(a) and (b) – Required by March 31, 2021 & January 1, 2023)
Appendix 3 | Q14 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.b.i.a.; S5.C.1.b.i.b. | Did you submit a report as described in S5.C.1.b.i(b)? (Required no later than January 1, 2023)
Appendix 3 | Q15 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.c.i. | Continue to design and implement local development-related codes, rules, standards, or other enforceable documents to minimize impervious surfaces, native vegetation loss, and stormwater runoff, where feasible? See S5.C.1.c.i. (Required annually)
Appendix 3 | Q16 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.c.i. | From the assessment described in S5.C.1.c.i(a), did you identify any administrative or regulatory barriers to implementation of LID Principles or LID BMPs? (Required annually)
Appendix 3 | Q16a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.c.i. | If yes, describe the barrier(s) and the measures taken to address them. (S5.C.1.c.i(a))
Appendix 3 | Q17 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.d.i. | Developed a watershed inventory as outlined in S5.C.1.d.i? (Submitted by March 31, 2022)
Appendix 3 | Q17a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.d.i. | Attach watershed inventory as described in S5.C.1.d.i.
Appendix 3 | Q18 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.d.ii.(a-c) | Developed a receiving water prioritization method and process as described in S.5.C.1.d.ii(a)-(c)? (Required by June 30, 2022.)
Appendix 3 | Q18a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.d.ii.(a-c) | Attach receiving water priority ranking process as described in S.5.C.1.d.ii(a)-(c).
Appendix 3 | Q19 | Annual Report Questions for Cities, Towns and Counties | S5.C.1.d.iii. | Developed a Stormwater Management Action Plan (SMAP) for at least one high priority area? (S.5.C.1.d.iii – Required by March 31, 2023)
Appendix 3 | Q19a | Annual Report Questions for Cities, Towns and Counties | S5.C.1.d.iii. | Attach SMAP(s)
Appendix 3 | Q20 | Annual Report Questions for Cities, Towns and Counties | S5.C.2. | Did you choose to adopt one or more elements of a regional program? (S5.C.2)
Appendix 3 | Q20a | Annual Report Questions for Cities, Towns and Counties | S5.C.2. | If yes, list the elements, and the regional program.
Appendix 3 | Q21 | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.i. | Attach a description of general awareness efforts conducted, including your target audiences and subject areas, per S5.C.2.a.i.
Appendix 3 | Q22 | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.ii.b. | Conducted an evaluation of the effectiveness of the ongoing behavior change program and documented recommendations as outlined in S.5.C.2.a.ii.(b). (Required no later than July 1, 2020)
Appendix 3 | Q22a | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.ii.b. | If not, explain
Appendix 3 | Q23 | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.ii.c. | Developed a behavior change campaign that is tailored to the community in accordance with S5.C.2.a.ii.(c)? (Required no later than February 1, 2021)
Appendix 3 | Q23a | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.ii.c. | Attach the strategy and schedule developed in accordance with S5.C.2.a.ii.(c).
Appendix 3 | Q24 | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.ii.c.; S5.C.2.a.ii.d. | Began implementing strategy outlined in S.5.C.2.a.ii(c) (S5.C.2.a.ii.(d) – Required by April 1, 2021)
Appendix 3 | Q25 | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.ii.e. | Attach the report developed in accordance with S5.C.2.a.ii.(e), which evaluated the changes in understanding and adoption of targeted behaviors resulting from the implementation of the strategy and any planned or recommended changes to the program in order to be more effective. (Required no later March 31, 2024)
Appendix 3 | Q26 | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.iii. | Promoted stewardship opportunities (or partnered with others) to encourage resident participation in activities such as those described in S5.C.2.a.iii.
Appendix 3 | Q26a | Annual Report Questions for Cities, Towns and Counties | S5.C.2.a.iii. | Attach a list of stewardship opportunities promoted.
Appendix 3 | Q27 | Annual Report Questions for Cities, Towns and Counties | S5.C.3.a. | Describe in Comments field the opportunities created for the public, including overburdened communities, to participate in the decision-making processes involving the development, implementation, and updates of the Permittee’s SWMP and the SMAP. (S5.C.3.a)
Appendix 3 | Q28 | Annual Report Questions for Cities, Towns and Counties | S5.C.3.b. | Posted the updated SWMP Plan and latest annual report on your website no later than May 31 of each year?. (S5.C.3.b)
Appendix 3 | Q28a | Annual Report Questions for Cities, Towns and Counties | S5.C.3.b. | List the website address in Comments field
Appendix 3 | Q29 | Annual Report Questions for Cities, Towns and Counties | S5.C.4.a.i-vii. | Maintained a map of the MS4 including the requirements listed in S5.C.4.a.i-vii?
Appendix 3 | Q30 | Annual Report Questions for Cities, Towns and Counties | S5.C.4.b.i. | Started mapping outfall size and material in accordance with S5.C.4.b.i? (Required no later than January 1, 2020)
Appendix 3 | Q30a | Annual Report Questions for Cities, Towns and Counties | S5.C.4.b.i. | Attach a spreadsheet that lists the known outfalls’ size and material(s).
Appendix 3 | Q31 | Annual Report Questions for Cities, Towns and Counties | S5.C.4.b.ii. | Completed mapping connections to private storm sewers in accordance with S5.C.4.b.ii? (Required no later than August 1, 2023)
Appendix 3 | Q32 | Annual Report Questions for Cities, Towns and Counties | S5.C.4.c. | Developed an electronic format for map, with fully described mapping standards in accordance with S5.C.4.c? (Required no later than August 1, 2021)
Appendix 3 | Q33 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.b. | Informed public employees, businesses, and the general public of hazards associated with illicit discharges and improper disposal of waste. Describe actions in Comments field. (S5.C.5.b)
Appendix 3 | Q34 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.c. | Implemented an ordinance or other regulatory mechanism to effectively prohibit non-stormwater, illicit discharges as described in S5.C.5.c.
Appendix 3 | Q35 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.d.i. | Implemented procedures for conducting illicit discharge investigations in accordance with S5.C.5.d.i.
Appendix 3 | Q35a | Annual Report Questions for Cities, Towns and Counties | S5.C.5.d.i. | Cite field screening methodology in Comments field.
Appendix 3 | Q36 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.d.i. | Percentage of MS4 coverage area screened in the reporting year per S5.C.5.d.i. (Required to screen 12% on average each year.)
Appendix 3 | Q36a | Annual Report Questions for Cities, Towns and Counties | S5.C.5.d.i. | Cite field screening techniques used to determine percent of MS4 screened.
Appendix 3 | Q37 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.d.i. | Percentage of total MS4 screened from permit issuance through the end of the reporting year. (S5.C.5.d.i.)
Appendix 3 | Q38 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.d.ii. | Describe how you publicized a hotline telephone number for public reporting of spills and other illicit discharges in the Comments field. (S5.C.5.d.ii)
Appendix 3 | Q39 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.d.iii. | Implemented an ongoing illicit discharge training program for all municipal field staff per S5.C.5.d.iii.
Appendix 3 | Q40 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.e. | Implemented an ongoing program to characterize, trace, and eliminate illicit discharges into the MS4 per S5.C.5.e.
Appendix 3 | Q41 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.f. | Municipal illicit discharge detection staff trained to conduct illicit discharge detection and elimination activities as described in S5.C.5.f.
Appendix 3 | Q42 | Annual Report Questions for Cities, Towns and Counties | S5.C.5.g.; Appendix 12 | Attach a report with data describing the actions taken to characterize, trace, and eliminate each illicit discharge reported to, or investigated by, the Permittee as described in S5.C.5.g. The submittal must include all of the applicable information and must follow the instructions, timelines, and format described in Appendix 12.
Appendix 3 | Q43 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.b.i-iii. | Implemented an ordinance or other enforceable mechanism to effectively address runoff from new development, redevelopment, and construction sites per the requirements of S5.C.6.b.i-iii.
Appendix 3 | Q44 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.b.i-iii. | Revised ordinance or other enforceable mechanism to effectively address runoff from new development, redevelopment, and construction sites per the requirements of S5.C.6.b.i-iii. (Required no later than June 30, 2022)
Appendix 3 | Q44a | Annual Report Questions for Cities, Towns and Counties | S5.C.6.b.i-iii. | Cite code reference in Comments field.
Appendix 3 | Q45 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.b.i.; Section 5 of Appendix 1 | Number of adjustments granted to the minimum requirements in Appendix 1. (S5.C.6.b.i. and Section 5 of Appendix 1)
Appendix 3 | Q46 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.b.i.; Section 6 of Appendix 1 | Number of exceptions/variances granted to the minimum requirements in Appendix 1. (S5.C.6.b.i, and Section 6 of Appendix 1)
Appendix 3 | Q47 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.i. | Reviewed Stormwater Site Plans for all proposed development activities that meet the thresholds adopted pursuant to S5.C.6.b.i. (S5.C.6.c.i)
Appendix 3 | Q47a | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.ii. | Number of site plans reviewed during the reporting period.
Appendix 3 | Q48 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.ii. | Inspected, prior to clearing and construction, permitted development sites per S5.C.6.c.ii, that have a high potential for sediment transport as determined through plan review based on definitions and requirements in Appendix 7 – Determining Construction Site Sediment Damage Potential?
Appendix 3 | Q48a | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.ii. | If no, inspected prior to clearing and construction, all construction sites meeting the minimum thresholds (S5.C.6.c.ii)?
Appendix 3 | Q49 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.iii. | Inspected permitted development sites during construction to verify proper installation and maintenance of required erosion and sediment controls per S5.C.6.c.iii.
Appendix 3 | Q49a | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.iii. | Number of construction sites inspected per S5.C.6.c.iii.
Appendix 3 | Q49b | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.iv. | Inspected stormwater treatment and flow control BMPs/facilities and catch basins in new residential developments every 6 months per S5.C.6.c.iv?
Appendix 3 | Q50 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.v. | Inspected all permitted development sites upon completion of construction and prior to final approval or occupancy to ensure proper installation of permanent stormwater facilities. (S5.C.6.c.v)
Appendix 3 | Q51 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.v. | Verified a maintenance plan is completed and responsibility for maintenance is assigned for projects prior to final approval and occupancy being granted. (S5.C.6.c.v)
Appendix 3 | Q52 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.ii-iv.; S5.C.7.c.viii. | Number of enforcement actions taken during the reporting period (based on construction phase inspections at new development and redevelopment projects per S5.C.6.c.ii-iv). (S5.C.7.c.viii)
Appendix 3 | Q53 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.c.vi | Achieved at least 80% of scheduled construction-related inspections. (S5.C.6.c.vi)
Appendix 3 | Q54 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.d. | Made Ecology’s Construction Stormwater General Permit Notice of Intent and the Industrial Stormwater General Permit Notice of Intent available to representatives of proposed new development and redevelopment? (S5.C.6.d)
Appendix 3 | Q55 | Annual Report Questions for Cities, Towns and Counties | S5.C.6.e. | All staff whose primary job duties are implementing the program to control stormwater runoff from new development, redevelopment, and construction sites including permitting, plan review, construction site inspections, and enforcement are trained to conduct these activities? (S5.C.6.e)
Appendix 3 | Q56 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.a. | Implemented maintenance standards that are as protective, or more protective, of facility function than those specified in the Stormwater Management Manual for Western Washington or a Phase I program approved by Ecology per S5.C.7.a.?
Appendix 3 | Q57 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.a. | Updated maintenance standards specified in Stormwater Management Manual for Western Washington per S5.C.7.a? (Required no later than June 30, 2022)
Appendix 3 | Q58 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.a. | Applied a maintenance standard for a facility or facilities which do not have maintenance standards specified in the Stormwater Management Manual for Western Washington? If so, note in the Comments field what kinds of facilities are covered by this alternative standard. (S5.C.7.a)
Appendix 3 | Q59 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.a.ii. | Verified that maintenance was performed per the schedule in S5.C.7.a.ii, when an inspection identified an exceedance of the maintenance standard.
Appendix 3 | Q59a | Annual Report Questions for Cities, Towns and Counties | S5.C.7.a.ii. | Attach documentation of maintenance time frame exceedances that were beyond the Permittee's control.
Appendix 3 | Q60 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.b.i.a. | Implemented an ordinance, or other enforceable mechanisms, to verify long-term operation and maintenance of stormwater treatment and flow control BMPs/facilities regulated by the Permittee per S5.C.7.b.i(a)?
Appendix 3 | Q61 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.b.i.(b) | Annually inspected stormwater treatment and flow control BMPs/facilities regulated by the Permittee per S5.C.7.b.i(b).
Appendix 3 | Q61a | Annual Report Questions for Cities, Towns and Counties | S5.C.7.b.i.(b) | If using reduced inspection frequency for the first time during this permit cycle, attach documentation per S5.C.7.b.i(b).
Appendix 3 | Q62 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.b.ii. | Achieved at least 80% of scheduled inspections to verify adequate long-term O&M. (S5.C.7.b.ii)
Appendix 3 | Q63 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.i. | Annually inspected all municipally owned or operated stormwater treatment and flow control BMPs/facilities? (S5.C.7.c.i)
Appendix 3 | Q63a | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.i. | Number of known stormwater treatment and flow control BMPs/facilities owned or operated by the Permittee.
Appendix 3 | Q63b | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c. | Number of facilities inspected during the reporting period.
Appendix 3 | Q63c | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c. | Number of facilities for which maintenance was performed during the reporting period.
Appendix 3 | Q64 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.i. | If using reduced inspection frequency for the first time during this permit cycle, attach documentation per S5.C.7.c.i.
Appendix 3 | Q65 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.ii. | Conducted spot checks and inspections, if necessary, of potentially damaged stormwater facilities after major storms as per S5.C.7.c.ii.
Appendix 3 | Q66 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.iii. | Inspected catch basins owned or operated by the Permittee every two years or used an alternative approach? (S.5.C.7.c.iii)
Appendix 3 | Q66a | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.iii. | Number of known catch basins?
Appendix 3 | Q66b | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.iii. | Number of catch basins inspected during the reporting period?
Appendix 3 | Q66c | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.iii. | Number of catch basins cleaned during the reporting period?
Appendix 3 | Q67 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.c.iii. | Attach documentation of alternative catch basin inspection approach for those owned or operated by the Permittee if used. (S5.C.7.c.iii)
Appendix 3 | Q68 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.d. | Implemented practices, policies, and procedures to reduce stormwater impacts associated with runoff from all lands owned or maintained by the Permittee, and road maintenance activities under the functional control of the Permittee. (S5.C.7.d)
Appendix 3 | Q69 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.d. | Documented practices, policies, and procedures to reduce stormwater impacts associated with runoff from all lands owned or maintained by the Permittee, and road maintenance activities under the functional control of the Permittee. (S5.C.7.d – Required by December 31, 2022)
Appendix 3 | Q69a | Annual Report Questions for Cities, Towns and Counties | S5.C.7.d. | Cite documentation in Comments.
Appendix 3 | Q70 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.e. | Implemented an ongoing training program for Permittee employees whose primary construction, operations or maintenance job functions may impact stormwater quality. (S5.C.7.e)
Appendix 3 | Q71 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.f. | Implemented a Stormwater Pollution Prevention Plan (SWPPP) for all heavy equipment maintenance or storage yards, and material storage facilities owned or operated by the Permittee in areas subject to this Permit that are not required to have coverage under an NPDES permit that covers stormwater discharges associated with the activity. (S5.C.7.f)
Appendix 3 | Q72 | Annual Report Questions for Cities, Towns and Counties | S5.C.7.f. | Updated, if needed, SWPPPs according to S5.C.7.f no later than December 31, 2022
Appendix 3 | Q73 | Annual Report Questions for Cities, Towns and Counties | S5.C.8.b.i. | Adopted ordinance(s), or other enforceable documents, requiring the application of source control BMPs for pollutant generating sources associated with existing land uses and activities per S.5.C.8.b.i. Cite ordinance in Comments field. (Required by August 1, 2022)
Appendix 3 | Q74 | Annual Report Questions for Cities, Towns and Counties | S5.C.8.b.ii. | Established an inventory per S5.C.8.b.ii. (Required by August 1, 2022)
Appendix 3 | Q74a | Annual Report Questions for Cities, Towns and Counties | S5.C.8.b.ii. | Number of total sites identified for the inventory.
Appendix 3 | Q75 | Annual Report Questions for Cities, Towns and Counties | S5.C.8.b.ii.a. | Implemented an inspection program per S5.C.8.b.iii. (Required by January 1, 2023)
Appendix 3 | Q76 | Annual Report Questions for Cities, Towns and Counties | S5.C.8.b.iv. | Implemented a progressive enforcement policy per S5.C.8.b.iv. (Required by January 1, 2023)
Appendix 3 | Q77 | Annual Report Questions for Cities, Towns and Counties | S5.C.8.b.iii.; S5.C.8.b.iv. | Attach a summary of actions taken to implement the source control program per S5.C.8.b.iii and S5.C.8.b.iv.
Appendix 3 | Q78 | Annual Report Questions for Cities, Towns and Counties | S5.C.8.b.iii. | Attach a list of inspections, per S5.C.8.b.iii, organized by the business category, noting the number of times each business was inspected and if enforcement actions were taken.
Appendix 3 | Q79 | Annual Report Questions for Cities, Towns and Counties | S5.C.8.b.v. | Implemented an ongoing source control training program per S5.C.8.b.v?
Appendix 3 | Q80 | Annual Report Questions for Cities, Towns and Counties | S7.A.; Appendix 2 | Complied with the Total Maximum Daily Load (TMDL)-specific requirements identified in Appendix 2. (S7.A)
Appendix 3 | Q80a | Annual Report Questions for Cities, Towns and Counties | S7.A.; Appendix 2 | List any requirements that were not met.
Appendix 3 | Q81 | Annual Report Questions for Cities, Towns and Counties | S7.A.; Appendix 2 | For TMDLs listed in Appendix 2: Attach a summary of relevant SWMP and Appendix 2 activities to address the applicable TMDL parameter(s). (S7.A)
Appendix 3 | Q82 | Annual Report Questions for Cities, Towns and Counties | S8.A.1.; S8.A.2.a. | Submitted payment for cost-sharing for Stormwater Action Monitoring (SAM) status and trends monitoring no later than December 1, 2019 (S8.A.1); and no later than August 15 of each subsequent year. (S8.A.2.a)
Appendix 3 | Q83 | Annual Report Questions for Cities, Towns and Counties | S8.A.2.a.; S8.A.2.b. | Notified Ecology by December 1, 2019, which option you selected: S8.A.2.a or S8.A.2.b.
Appendix 3 | Q84 | Annual Report Questions for Cities, Towns and Counties | S8.B.1.; S8.B.2.a. or S8.B.2.b. | Submitted payment for cost-sharing for SAM effectiveness and source identification studies no later than December 1, 2019 (S8.B.1); and no later than August 15 of each subsequent year. (S8.B.2.a or S8.B.2.b)
Appendix 3 | Q85 | Annual Report Questions for Cities, Towns and Counties | S8.B.2. | Notified Ecology by December 1, 2019, which option you selected: S8.B.2.a or S8.B.2.b.
Appendix 3 | Q86 | Annual Report Questions for Cities, Towns and Counties | S8.C.1.; S8.C.1.b; Appendix 9 | If conducting stormwater discharge monitoring in accordance with S8.C.1., submitted a QAPP to Ecology no later than February 1, 2020? (S8.C.1.b and Appendix 9)
Appendix 3 | Q87 | Annual Report Questions for Cities, Towns and Counties | S8.C.1. | If conducting stormwater discharge monitoring in accordance with S8.C.1., attach a data and analysis report per S8.C.1 and Appendix 9. (Due annually beginning March 31, 2021)
Appendix 3 | Q88 | Annual Report Questions for Cities, Towns and Counties | G3.B. | Notified Ecology in accordance with G3 of any discharge into or from the Permittees MS4 which could constitute a threat to human health, welfare, or the environment. (G3)
Appendix 3 | Q89 | Annual Report Questions for Cities, Towns and Counties | G3.A. | Took appropriate action to correct or minimize the threat to human health, welfare, and/or the environment, per G3.A.
Appendix 3 | Q90 | Annual Report Questions for Cities, Towns and Counties | S4.F.1. | Notified Ecology within 30 days of becoming aware that a discharge from the Permittee’s MS4 caused or contributed to a known or likely violation of water quality standards in the receiving water. (S4.F.1)
Appendix 3 | Q91 | Annual Report Questions for Cities, Towns and Counties | S4.F.3.a. | If requested, submitted an Adaptive Management Response report in accordance with S4.F.3.a.
Appendix 3 | Q92 | Annual Report Questions for Cities, Towns and Counties | S4.F.3.d. | Attach a summary of the status of implementation of any actions taken pursuant to S4.F.3 and the status of any monitoring, assessment, or evaluation efforts conducted during the reporting period. (S4.F.3.d)
Appendix 3 | Q93 | Annual Report Questions for Cities, Towns and Counties | G20 | Notified Ecology of the failure to comply with permit terms and conditions within 30 days of becoming aware of the non-compliance. (G20)
Appendix 3 | Q94 | Annual Report Questions for Cities, Towns and Counties | G20 | Number of non-compliance notifications (G20) provided in reporting year. List permit conditions described in non-compliance notification(s) in Comments field.